## CP Summary
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
|  | Collaborative Productivity | Via organisations working collaboratively, cost and efficiency improvements can be made across the SEL system. | 1
Leadership |  | SRO: | Programme Managers: | Current delivery level:
|  | Martin Shaw | TBC - Programme Managers to be established for each CP workstream. | SEL led programme
Background |  | Collaborative Productivity is one of three broad programmes of work within the Our Healthier South East London (OHSEL) strategy. It was a critical component of the Sustainability and Transformation Plan (STP) submitted to NHS England in June 2016 and represents a significant factor in securing an allocation of the £1.8bn Transformation Fund on offer, in part to enable systems to deliver the benefits espoused in their place-based plans. The six organisations (GSTT, KCH, DGT, LGT, SLaM and Oxleas) have collectively concluded that collaboration can no longer be overlooked as a means to deriving savings and ensuring financial sustainability long term. There are existing examples of collaboration within the collective. Building on this foundation, there are significant savings to be made in extending current initiatives across the patch.
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any |  | Case for change documents attached?
|  | The new era of place-based planning and Sustainability and Transformation Plan (STP) ‘footprints’ means individual organisations are no longer just responsible for performance within their own organisation. All entities are now duty bound to take on wider responsibility and ensure the system as a whole is viable, resilient and performing as expected. The focus on operational performance improvement within any organisation remains important, but we want to make a move from in-year, organisational savings to longer term transformation and strategic planning across the economy to achieve what is required. At the moment, the six organisations work independently with little interactions. Processes and systems are duplicated and often inefficient. Collaboration, including consolidation and standardisation, will lead to improved performance, greater efficiences as well as financial savings. [attached document: CP summary report] |  | Yes, attached. See case for change document and May 2016 Collaborative Productivity report
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme in 16-17 and/or 17-18 to 18-19? |  | Is the Financial case attached?
|  | As outlined in the STP, the majority of the affordability challenge in south east London can be closed through collaborative productivity and service transformation/pathway redesign. The savings are calculated against the FY21 ‘status quo’ affordability challenge of £676m after business as usual CIPs (at 1.6% p.a.). Following savings of £230m associated with collaborative productivity work (not including savings from Dartford and Gavesham) and further planned savings of £113m associated with service transformation and pathway redesign, a residual challenge of £333m still remains. Of this residual challenge £190m relates to the commissioning of specialised activity (an area of focus for the programme going forwards) and just under £66m was received by the system as sustainability and transformation funding in FY17. Therefore £77m (or ~1% of system-wide revenue) remains to be addressed locally. |  | Yes, attached. See case for change document and May 2016 Collaborative Productivity report
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
|  | There is agreement that there is a need to push this work forward and start pushing for tangible changes and results. We have decided to move forward with business cases for four areas, HR, Finance, Procurement and Bank and agency . HR and Finance business cases will be completed in October while the others will be completed in December. A futher business case has yet to be identified. Discussions are also being held about dedicating sufficient time and resources to this programme, including looking at full-time ring-fenced resources. |  | No attachment
Other programmes or Sub-programmes whose delivery contributes to the overall programme |  | Please list any sub-programmes, themes or other plans which need describing in greater detail elsewhere? |  | Is there a delivery plan for this sub-programme?
| 1 | Collective buying power |  | Yes, completed
| 2 | Collective Estates |  | Yes, completed
| 3 | Standardise and consolidate non-clinical support services |  | Yes, completed
| 4 | Consolidate clinical support services |  | Yes, completed
| 5 | Optimise the workforce |  | Yes, completed
6
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available? |  | Governance diagram attached?
|  | The current governance is focused around a Provider Collaboration Steering Group comprised of the Directors of Finance (DoF) from each provider (the structure of which is included below). The OHSEL programme is in the process of setting up a Productivity Board, which the Steering Group will be held accountable to, and will provide further direction and drive. The board will include specialist input that the system will need to draw upon as we move forward, such as Union and HR representation. Currently Martin Shaw is the overall Senior Responsible Officer (SRO) for the productivity programme. Each productivity area is then led by a Provider DoF as SRO. Within each area we have established a Subject Matter Expert (SME) lead and, to ensure input and representation from each organisation, we also identified working groups for each opportunity. |  | Yes, attached. See case for change document chapter 4
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | Reduce costs and improve efficiency by sharing administrative and back office functions across sites, including procurement, and rationalising collective estates.
| 2 | Develop and implement networking of clinical support services so as to protect and improve the quality of services to patients, while making the most efficient use of the available workforce and capacity.
| 3 | Make more efficient use of the SEL healthcare workforce reducing administrative burden on frontline staff and reducing agency spend.
| 4 | Continue to build and strengthen the collaborative culture that exists among SEL providers. This will mean that providers consider and promote the interests of the SEL sector as a whole, in addition to fulfilling the obligations they have to their individual organisations.
Constraints to 2021 (in order of scale, most impactful first, one per cell) | 1 | Lack of dedicated resources- Currently, all resources involved carry out the work above and beyond their day-to-day tasks. This results in work not being done as quickly as it could be and the programme not having enough traction and momentum to move forward. Dedicated resources will need to be secured to mitigate this.
| 2 | Funding/investment - The work is based on the assumption of receiving STF as well as obtaining additional funds from other means. If these funds are not secured, the programme may fail to run.
| 3 | Existing infrastructure/agreements - Any existing agreements (e.g. fixed term contracts) may result in difficulties in making drastic changes, consolidating functions and working collaboratively as it may not be possible or may result in hefty penalties.
Assumptions to 2021 (including re enablers, in order of scale, most impactful first, one per cell) | 1 | Integrated technological systems will be put in place
| 2 | Ensuring access to Transformation funding
| 3 | Digital health technology investment will be sourced and available
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
| 1 | Lack of resources available in the system | Identify dedicated resources and ensure time is protected | 1
| 2 | Lack of investment funds | Careful budgeting and usage of available funds including STF | 1
Is there anything else you think we should be looking into / considering (including opportunities or initiatives)? |  | n/a
Name of person who completed this document: |  |  | Email address:
Organisation: |  |  | Telephone number:

## Back Office
Back Office | [17 empty] | Back Office
STP DELIVERY AND FINANCIAL PLAN
SRO |  | SME |  | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address: | [14 empty] | **These estimates have been based on the May 2016 report and have used a top-down approach; further analysis is being carried out.
Martin Shaw |  | Ann MacIntyre (HR), Martin Chamberlain and Daniel Carlen (Finance), Stephen Docherty (IT) | [9 empty] | Organisation: |  |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cumulative impact | [6 empty] | DELIVERABLES: What will be delivered or produced as a result of this initiative (to achieve quality, operating plan requirements and/or outcomes)? | [5 empty] | DEPENDENCIES | CONSTRAINTS | ENABLERS | [5 empty] | RISKS |  |  |  | *2016-17 |  | *2017-18 |  | *2018-19 |  | *2019-20 |  | *2020-21
# | Sub-workstream or initiative (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key outcome(s) or goal(s) (one per cell) | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Constraints (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Risk description | RAG rating (likelihood) | Mitigation | Mitigation required by (date) | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£
1 | One consolidated finance function that provides finance as a service to SEL providers. | Carter recommendations to reduce corporate and administrative costs to 7% of income by 2018 and 6% by 2020 | Cost reduction of between 20%-40% | Cost Saving | 0% | 10% | 10% | 80% | 100% | 2020/21 | Fair achievement | Investment ready business case for consolidated SEL finance department for providers | Q1, 2017-18 | Design specification and structure of consolidated SEL finance department for providers | Q1, 2018-19 | Implementation of consolidated SEL finance department for providers | Q2, 2019-20 | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system. | Availability of dedicated resources to move forward the business cases and implementation of these schemes | Technology platforms that enable teams to collaborate effectively | Q1, 2019-20 | Engagement and sign off from key stakeholders of operating model | Q1, 2017-18 |  |  | Non approval of business case | 2 | Constant stakeholder engagement | Q1, 2017-18 | 200000 | 600000 | 16000000 | 4900000 | 7600000 | 13700000 | - | 21700000 | - | 38200000
|  | Case study evidence base including examples from NHS SBS, Hoople Ltd and Cambridgeshire and Northampton County Councils Project | Standardised reporting across trusts leading to easier comparability of positions and easier collaboration on other projects | Improved quality | [13 empty] | Willingness of senior stakeholders to take ownership and drive through to delivery | [7 empty] | Challenges associated with staff transitioning roles and redundancies | 2 | Strong communications with staff throughout process. Legal advice will also be sought | Q1, 2018-19
|  | Engagement with Finance Directors of the 6 SEL providers | [23 empty] | Flow of accurate, timely financial information is disrupted | 1 | Detailed design phase as well as short phase of double running | Q1, 2018-19
2 | One consolidated HR function that provides finance as a service to SEL providers. | Carter recommendations to reduce corporate and administrative costs to 7% of income by 2018 and 6% by 2020 | Cost reduction of between 20%-40% | Cost Saving | 0% | 10% | 10% | 80% | 100% | 2020/21 | Fair achievement | Investment ready business case for consolidated SEL HR department for providers | Q1, 2017-18 | Design specification and structure of consolidated SEL HR department for providers | Q1, 2018-19 | Implementation of consolidated SEL HR department for providers | Q2, 2019-20 | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system. | Availability of dedicated resources to move forward the business cases and implementation of these schemes | Technology platforms that enable teams to collaborate effectively | Q1, 2019-20 | Engagement and sign off from key stakeholders of operating model | Q1, 2017-18 |  |  | Non approval of business case | 2 | Constant stakeholder engagement | Q1, 2017-18
|  | Case study evidence base including examples from NHS SBS, Hoople Ltd and Cambridgeshire and Northampton County Councils Project | [15 empty] | Willingness of senior stakeholders to take ownership and drive through to delivery | [7 empty] | Challenges associated with staff transitioning roles and redundancies | 2 | Strong communications with staff throughout process. Legal advice will also be sought | Q1, 2018-19
Engagement with Ann MacInytre (Director of Workforce and Organisation for GSTT)
|  | Carter recommendations to reduce corporate and administrative costs to 7% of income by 2018 and 6% by 2020 | Cost reduction of between 20%-40% | Cost Saving | 0% | 10% | 10% | 80% | 100% | 2020/21 | Fair achievement | Investment ready business case for consolidated SEL procurement department for providers | Q1, 2017-18 | Implement Virtual Stock cloud based purchase-to-pay system sector wide and centralise the transaction and catalogue management functions | Q1, 2018-19 | Implement Omnicell inventory management system sector wide | Q3, 2018-19 | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system. | Availability of dedicated resources to move forward the business cases and implementation of these schemes | Availability of purchase-to-pay system | Q3, 2017-18 | Availability of inventory management system | Q1, 2018-19 |  |  | Non approval of business case | 2 | Constant stakeholder engagement | Q4, 2016-17
|  | Case study evidence base including examples from NHS SBS, Hoople Ltd and Cambridgeshire and Northampton County Councils Project | Utilise the increased economies of scale to drive down unit prices | [14 empty] | Willingness of senior stakeholders to take ownership and drive through to delivery | [7 empty] | Challenges associated with staff transitioning roles and redundancies | 2 | Strong communications with staff throughout process. Legal advice will also be sought | Q1, 2018-19
|  | Engagement with Ann MacInytre (Director of Workforce and Organisation for GSTT) | [23 empty] | Disruption to procurement pathways in the transition | 3 | Detailed design phase as well as short phase of double running
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework
n/a | [11 empty] | n/a

## Collective buying power
Collective buying power | [11 empty] | Collective buying power | [7 empty] | Collective buying power | [9 empty] | Collective buying power
STP DELIVERY AND FINANCIAL PLAN
SRO |  | SME |  | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address: | [14 empty] | **These estimates have been based on the May 2016 report and have used a top-down approach; further analysis is being carried out.
John Hennesey |  | David Lawson | [9 empty] | Organisation: |  |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cumulative impact | [6 empty] | DELIVERABLES: What will be delivered or produced as a result of this initiative (to achieve quality, operating plan requirements and/or outcomes)? | [5 empty] | DEPENDENCIES | CONSTRAINTS | ENABLERS | [5 empty] | RISKS |  |  |  | *2016-17 |  | *2017-18 |  | *2018-19 |  | *2019-20 |  | *2020-21
# | Sub-workstream or initiative (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key outcome(s) or goal(s) (one per cell) | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Constraints (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Risk description | RAG rating (likelihood) | Mitigation | Mitigation required by (date) | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£
1 | A hybrid approach to procurement: common elements of supply chain are delivered within a centralised function and cross-Trust Category Management helps to harness the economies of scale | Carter recommendations on purchase-to-pay systems and capitalising on the national nature of the NHS | Reduction in waste by between 8%-3% | Cost reduction | 0% | 25% | 50% | 75% | 100% | 2020/21 | Fair achievement | Procurement outline business case | Q4, 2016-17 | Implement Virtual Stock cloud based purchase-to-pay system sector wide and centralise the transaction and catalogue management functions | Q1, 2018-19 | Implement Omnicell inventory management system sector wide | Q3, 2018-19 | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system. | Availability of dedicated resources to move forward the business cases and implementation of these schemes | Availability of purchase-to-pay systems | Q1, 2018-19 | Availability of inventory management systems | Q3, 2018-19 |  |  | Non approval of business case | 2 | Constant stakeholder engagement | Q4, 2016-17 | 1700000 | 9900000 | 2600000 | 33800000 | 800000 | 42300000 | 800000 | 51600000 | 800000 | 61700000
|  | Case studies including London Procurement Partnership, Mental Health Trust clustering and Pan-Shelford Procurement Strategy | Reduction in unit price by 5%-3% | [14 empty] | Willingness of senior stakeholders to take ownership and drive through to delivery | [7 empty] | Challenges associated with staff transitioning roles and redundancies | 2 | Strong communications with staff throughout process. Legal advice will also be sought | Q3, 2016-17
[26 empty] | Disruption to procurement pathways in the transition | 3 | Detailed design phase as well as short phase of double running | Q3, 2016-17
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework
n/a

## Estates
Estates | [11 empty] | Estates | [7 empty] | Estates | [9 empty] | Estates
STP DELIVERY AND FINANCIAL PLAN
SRO |  | SME |  | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 1 | [5 empty] | Name of person who completed this document: |  |  | Email address: | [14 empty] | *These estimates have been based on the May 2016 report and have used a top-down approach; further analysis is being carried out.
Gus Heafield |  | TBC | [9 empty] | Organisation: |  |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cumulative impact | [6 empty] | DELIVERABLES: What will be delivered or produced as a result of this initiative (to achieve quality, operating plan requirements and/or outcomes)? | [5 empty] | DEPENDENCIES | CONSTRAINTS | ENABLERS | [5 empty] | RISKS |  |  |  | *2016-17 |  | *2017-18 |  | *2018-19 |  | *2019-20 |  | *2020-21
# | Sub-workstream or initiative (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key outcome(s) or goal(s) (one per cell) | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Constraints (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Risk description | RAG rating (likelihood) | Mitigation | Mitigation required by (date) | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£
1 | One, aligned estates strategy and establishing a Strategic Asset Management function | Carter benchmarks: with a maximum of 35% of non-clinical floor space and 2.5% of unoccupied or under-used space by April 2017 | Making real time transparent data and information a reality | Cost reduction | 0% | 20% | 70% | 90% | 100% | Q4, 2020-21 | Fair achievement | Establish SAM | Q3, 2020-21 | B2B asset sharing platform | Q3, 2020-21 | Funding and delivery models established | Q4, 2020-21 | Estates business cases/changes agreed on |  | Technology | Q4, 2017-18 | Contracting/commissioning | Q4, 2017-18 |  |  | Difficult to get complete consensus across system | 3 | Governance arrangements put in place | Q4, 2016-17 | 400000 | 0 | 1800000 | 0 | 1200000 | 12000000 | 1000000 | 12700000 | 300000 | 26800000
|  | Carter benchmarks: average estates and facilities (E&FM) running cost per m 2 should be £319 | Establishing a Strategic Asset Management (SAM) function to improve system-wide property management | [14 empty] | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system.
|  | Case studies: GSTT and DGT ACC Vanguard, Essentia, London Estates Group | Investing in a B2B asset sharing technology platform as a sustainable solution
Maximising productivity and utilisation of key operational areas
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework

## Clinical support
Clinical support | [11 empty] | Clinical support | [7 empty] | Clinical support | [9 empty] | Clinical support
STP DELIVERY AND FINANCIAL PLAN
SRO: |  | SME |  | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 1 | [5 empty] | Name of person who completed this document: |  |  | Email address: | [14 empty] | **These estimates have been based on the May 2016 report and have used a top-down approach; further analysis is being carried out.
Lorraine Clegg |  | Roger Fernandes (Pharmacy) | [9 empty] | Organisation: |  |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cumulative impact | [6 empty] | DELIVERABLES: What will be delivered or produced as a result of this initiative (to achieve quality, operating plan requirements and/or outcomes)? | [5 empty] | DEPENDENCIES | CONSTRAINTS | ENABLERS |  | ENABLERS (continued) |  |  |  | RISKS |  |  |  | *2016-17 |  | *2017-18 |  | *2018-19 |  | *2019-20 |  | *2020-21
# | Sub-workstream or initiative (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key outcome(s) or goal(s) (one per cell) | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Constraints (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Risk description | RAG rating (likelihood) | Mitigation | Mitigation required by (date) | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£
1 | Establish a collaborative clinical support service model within SEL e.g. ‘hub and spoke’ | SEL ambition | Demand is effectively managed across the patch | Current demand and capacity management | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | Establish a single delivery vehicle for hospital pharmacy services e.g. manufacturing and/or dispensing | Q4, 2017-18 | Establish a collaborative model of pathology provision e.g. hub (cold work) and spoke (hot / ESL). | Q4, 2017-18 | Establish a collaborative JV of optimally located satellite dialysis centres. | Q4, 2017-18 | Collective procurement is carried out on hospital pharmacy equipment and drugs | Some existing arrangements (e.g. Viapath) will need to be carefully considered | Technology | Q3, 2018-19 | Infrastructure (estates) | Q3, 2017-18 | Workforce | Q3, 2017-18 | Lack of dedicated resources to drive initiative forward | 1 | FDs to look into obtaining resources | Q4, 2016-17 | 900000 | 6000000 | 1000000 | 13800000 | 2900000 | 28000000 | 1100000 | 35700000 | 1000000 | 37700000
2 | A pan-SEL “federation” networked expertise within a SEL internal market | SEL ambition | Processes are leaner | Improved performance | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | [6 empty] | Appropriate information from providers are made available | [7 empty] | Lack of momentum/ desire for change due to existing agreements already in place | 2 | Stakeholder engagement to decide on path moving forward | Q3, 2017-18
|  |  | Services deliver wider commercial benefit | Improved outcomes | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | [6 empty] | STF Funding
|  |  | Expertise is fully networked | Improved performance | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement
|  |  | Workforce is multi-skilled | Improved quality | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement
|  |  | Investment in systems and equipment at scale | Future demand and capacity management | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework

## Workforce
Workforce | [11 empty] | Workforce | [7 empty] | Workforce | [9 empty] | Workforce
STP DELIVERY AND FINANCIAL PLAN
SRO |  | SME |  | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 1 | [5 empty] | Name of person who completed this document: |  |  | Email address: | [14 empty] | **These estimates have been based on the May 2016 report and have used a top-down approach; further analysis is being carried out.
Colin Gentile |  | Janet Lynch | [9 empty] | Organisation: |  |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cumulative impact | [6 empty] | DELIVERABLES: What will be delivered or produced as a result of this initiative (to achieve quality, operating plan requirements and/or outcomes)? | [5 empty] | DEPENDENCIES | CONSTRAINTS | ENABLERS |  | ENABLERS (continued) |  |  |  | RISKS |  |  |  | *2016-17 |  | *2017-18 |  | *2018-19 |  | *2019-20 |  | *2020-21
# | Sub-workstream or initiative (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key outcome(s) or goal(s) (one per cell) | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Constraints (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Risk description | RAG rating (likelihood) | Mitigation | Mitigation required by (date) | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£ | Revenue investment £ | Savings -£
1 | Promote productivity in outpatients | Case studies: based on a number of NHS Trusts that have achieved productivity gains in outpatients | Reduction in cost in outpatients | Cost reduction | 0% | 0% | 20% | 70% | 100% | Q1, 2020-21 | Poor achievement | Identification of pilot Trust/ward | Q2, 2017-18 | Implementation in pilot Trust | Q1, 2018-19 | Train the trainers programme to spread best practice from centre of excellence | Q1, 2019-20 | Agreement on pilot site | Appropriate skills to be able to drive productivity | Clear idea of current outpatient procedures | Q3, 2017-18 | Clear message from senior staff that initiatives to improve productivity must be given priority | Q1, 2018-19 |  |  | Inertial to changing processes and ways of working | 1 | Strong leadership from the top and experienced trainers in lean methodologies | Q1, 2018-19 | 800000 | 27300000 | 5200000 | 46300000 | 1800000 | 56500000 | 0 | 58500000 | 0 | 60800000
[26 empty] | Productivity is improved in pilot site but learning is not spread through SEL | 2 | Identify champions early and have detailed plan for second phase of spreading learning | Q1, 2019-20
2 | Reduce agency rates by collaborative planning and sharing of data | Case studies including GSTT and D&G ACC Vanguard and London HRD Network | One dashboard for SEL to compare bank and agency rates and costs | Cost reduction | 0% | 20% | 100% | 100% | 100% | Q1, 2018-19 | Poor achievement | Data agreement signed off for SEL | Q4, 2016-17 | Development of dashboard | Q2, 2017-18 |  |  | Approval of data sharing agreement | Availability of appropriate resource to build dashboard | Technology platform to host dashboard | Q2, 2017-18 |  |  |  |  | Dashboard is not used to drive down prices | 2 | Appoint an SRO and board who are tasked with driving down prices | Q2, 2017-18
|  | NHS Agency caps: Trusts should not pay an agency more than 55% more than a permanent member of staff would cost | [23 empty] | Data is collected in an inconsistent manor | 2 | Clear templates for trusts to populate | Q1, 2017-18
3 | Set up joint agency | Case studies including GSTT and D&G ACC Vanguard and London HRD Network | Creation of an independent but jointly owned agency who will provide a professional, affordable service to SEL providers | Cost reduction | 0% | 25% | 75% | 100% | 100% | Q1, 2019-210 | Fair achievement | Investment ready business case for joint agency | Q1, 2017-18 | Design specification and structure of joint agency | Q1, 2018-19 | Implementation of joint agency | Q2, 2019-20 | The scheme was originally predicated on the understanding that STP funding would be made available. It appears this is not the case and so the scheme will have to be financed from within the system. | Availability of appropriate resource to deliver business cases and design entity | Digital platform to deal with bookings and communicate with agency staff | Q2, 2019-20 | Organisation design expertise | Q1, 2018-19 |  |  | Difficulty in recruiting agency staff | 2 | Offer staff benefits such as training etc. and competitive pay packages | Q3, 2016-17
|  | NHS Agency caps: Trusts should not pay an agency more than 55% more than a permeant member of staff would cost | [23 empty] | Difficulty in commercial arrangements between Trusts | 2 | Gain outside support in drawing up clear commercial arrangements | Q2, 2019-20
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework
n/a | [11 empty] | n/a

## Menu (hidden)
Year | Year | Status | Priority | 16-17 | 17-18 | Current | 1 | Yes, attached | Programmes | Programme | Delivery level | 18-19 |  | 5 year | Word limits |  |  | Enablers | Impact | Savings badged
1 | 2016-17 | On track | High | 31/07/16 or earlier and overdue | 2017-04-30 | Opportunity Analysis | 2 | No attachment | Delivery model implementation – C&H | Environment, leisure and physical environment | Locally delivered programme with SEL line of sight | 2018-04-30 | National, mandatory | Q3, 2016-17 | words | characters | Domain 1 - Preventing people from dying prematurely: how successful the NHS is in reducing the number of avoidable deaths. | Technology | Activity shift | Health commissioner QIPP
2 | 2017-18 | Not on track but plan to recover | Medium | 2016-08-31 | 2017-05-31 | Implementation plan | 3 |  | Delivery model implementation – WEL | Early years, schools and healthy families | Locally delivered programme with SEL co-ordination | 2018-05-31 | National guideline or best practice | Q4, 2016-17 | 500 | 2700 | Domain 2 - Enhancing quality of life for people with long-term conditions: how successfully the NHS is supporting people with long-term conditions to live as normal a life as possible. | Infrastructure (estates) | Current demand and capacity management | Provider CIP - contributing to 2%
3 | 2018-19 | Not on track and no plan to recover | Low | 2016-09-30 | 2017-06-30 | Business Case |  |  | Delivery model implementation - BHR | Employment | SEL led programme | 2018-06-30 | London region, mandatory | Q1, 2017-18 | 250 | 1350 | Domain 3 - Helping people to recover from episodes of ill health or following injury: how people recover from ill health or injury and wherever possible how it can be prevented. | Workforce | Future demand and capacity management | Provider CIP - above 2%
4 | 2019-20 |  | TBC | 2016-10-31 | 2017-07-31 | Progress report | Good achievement |  | Prevention and wellbeing | Healthy living and smoking cessation |  | 2018-07-31 | London guideline or best practice | Q2, 2017-18 | 100 | 540 | Domain 4 - Ensuring that people have a positive experience of care: looks at the importance of providing a positive experience of care for patients, service users and carers. | Procurement | Improved outcomes | Existing transformation programme (eg TST, ACO)
5 | 20120-21 |  |  | 2016-11-30 | 2017-08-31 | No attachment | Fair achievement |  | Enhanced Primary care | Housing and planning |  | 2018-08-31 | SEL ambition | Q3, 2017-18 |  |  | Domain 5 - Treating and caring for people in a safe environment and protecting them from avoidable harm: explores patient safety and its importance in terms of quality of care to deliver better health outcomes. | Contracting/commissioning | Improved patient experience | Local authority
|  |  |  | 2016-12-31 | 2017-09-30 |  | Poor achievement | Yes, completed | Planned Care: maternity | Self-care management |  | 2018-09-30 |  | Q4, 2017-18 |  |  |  | Communications | Improved performance
|  |  |  | 2017-01-31 | 2017-11-30 |  | National outlier (poor) | Yes, partially completed | Planned Care: Cancer | Community based end of life care |  | 2018-10-31 |  | Q1, 2018-19 |  |  |  | Engagement | Improved quality
|  |  |  | 2017-02-28 | 2017-12-31 |  | N/A (new service) | No, to be completed | Planned Care: Surgery | Enhanced primary care |  | 2018-11-30 |  | Q2, 2018-19 |  |  |  |  | Service innovation
|  |  |  | 2017-03-31 | 2018-01-31 |  |  | Please refer to separate SRO |  | Reducing unnecessary diagnostics |  | 2018-12-31 |  | Q3, 2018-19
[5 empty] | 2018-02-28 |  |  |  | Unscheduled care | Pathway redesign and best in class clinical productivity, especially outpatient care |  | 2019-01-31 |  | Q4, 2018-19
[5 empty] | 2018-03-31 |  |  |  | Mental Health | Medicines management |  | 2019-02-28 |  | Q1, 2019-20
[9 empty] | Medicines management | High quality integrated mental health care and support |  | 2019-03-31 |  | Q2, 2019-20
[9 empty] | Procurement | Ambulatory care |  |  |  | Q3, 2019-20
[9 empty] | Bank & agency and back office (HR) | Integrated health and social care |  |  |  | Q4, 2019-20
[9 empty] | Back office (finance) | Integration children's and young people's care |  |  |  | Q1, 2020-21
[9 empty] | Back office (IT) | Transforming Sexual Health services |  |  |  | Q2, 2020-21
[9 empty] | Pathology | Localised programmes for learning disabilities |  |  |  | Q3, 2020-21
[9 empty] | Estates utilisation and productivity | Screening for cancer and other conditions |  |  |  | Q4, 2020-21
[9 empty] | Estates disposals | Integrated urgent and emergency care (including LAS)
[9 empty] | New capacity | Improving the treatment of cancer in community and secondary settings
[9 empty] | Cancer | Planned care strategy, including surgery
[9 empty] | Cardiac | Maternity
[9 empty] | Mental Health | Safely transitioning patients from King George Hospital's emergency dept
Renal
Neonatal
Communications
Digital
Finance
Workforce
Collaborative Productivity

## Backing sheet (hidden)
Programme | Programme | Vision | Is delivery of the aim on track? (RAG = 1,2,3) | SRO: | Delivery lead: | Current delivery level: | Background | Case for change | Case for change doc attached? | Financial case for change | Financial case for change doc attached? | Programme position Aug 16 | Programme position Aug 16 doc attached? | Workstream 1 | Workstream 1 doc attached? | Workstream 2 | Workstream 2 doc attached? | Workstream 3 | Workstream 3 doc attached? | Workstream 4 | Workstream 4 doc attached? | Workstream 5 | Workstream 5 doc attached? | Workstream 6 | Workstream 6 doc attached? | Workstream 7 | Workstream 7 doc attached? | Governance | Governance diagramme attached | Objective 1 | Objective 2 | Objective 3 | Objective 4 | Objective 5 | In scope | Out of scope | Constraint 1 | Constraint 2 | Constraint 3 | Constraint 4 | Constraint 5 | Assumption 1 | Assumption 2 | Assumption 3 | Assumption 4 | Assumption 5 | Risk 1 | Risk 1 Mitigation | Risk 1 score post mitigation | Risk 2 | Risk 2 Mitigation | Risk 2 score post mitigation | Risk 3 | Risk 3 Mitigation | Risk 3 score post mitigation | Risk 4 | Risk 4 Mitigation | Risk 4 score post mitigation | Risk 5 | Risk 5 Mitigation | Risk 5 score post mitigation | Deliverable 1 | Deliverable 1 target date | Deliverable 1 status | Deliverable 2 | Deliverable 2 target date | Deliverable 2 status | Deliverable 3 | Deliverable 3 target date | Deliverable 3 status | Deliverable 4 | Deliverable 4 target date | Deliverable 4 status | Deliverable 5 | Deliverable 5 target date | Deliverable 5 status | Anything else? | Who completed | Organisation | Email | Telephone number
0 | Collaborative Productivity | 0 | 1 | 0 | TBC - Programme Managers to be established for each CP workstream. | 0 | Collaborative Productivity is one of three broad programmes of work within the Our Healthier South East London (OHSEL) strategy. It was a critical component of the Sustainability and Transformation Plan (STP) submitted to NHS England in June 2016 and represents a significant factor in securing an allocation of the £1.8bn Transformation Fund on offer, in part to enable systems to deliver the benefits espoused in their place-based plans. The six organisations (GSTT, KCH, DGT, LGT, SLaM and Oxleas) have collectively concluded that collaboration can no longer be overlooked as a means to deriving savings and ensuring financial sustainability long term. There are existing examples of collaboration within the collective. Building on this foundation, there are significant savings to be made in extending current initiatives across the patch. | The new era of place-based planning and Sustainability and Transformation Plan (STP) ‘footprints’ means individual organisations are no longer just responsible for performance within their own organisation. All entities are now duty bound to take on wider responsibility and ensure the system as a whole is viable, resilient and performing as expected. The focus on operational performance improvement within any organisation remains important, but we want to make a move from in-year, organisational savings to longer term transformation and strategic planning across the economy to achieve what is required. At the moment, the six organisations work independently with little interactions. Processes and systems are duplicated and often inefficient. Collaboration, including consolidation and standardisation, will lead to improved performance, greater efficiences as well as financial savings. [attached document: CP summary report] | Yes, attached. See case for change document and May 2016 Collaborative Productivity report | There is agreement that there is a need to push this work forward and start pushing for tangible changes and results. We have decided to move forward with business cases for four areas, HR, Finance, Procurement and Bank and agency . HR and Finance business cases will be completed in October while the others will be completed in December. A futher business case has yet to be identified. Discussions are also being held about dedicating sufficient time and resources to this programme, including looking at full-time ring-fenced resources. | Yes, attached. See case for change document and May 2016 Collaborative Productivity report | There is agreement that there is a need to push this work forward and start pushing for tangible changes and results. We have decided to move forward with business cases for four areas, HR, Finance, Procurement and Bank and agency . HR and Finance business cases will be completed in October while the others will be completed in December. A futher business case has yet to be identified. Discussions are also being held about dedicating sufficient time and resources to this programme, including looking at full-time ring-fenced resources. | No attachment | Collective buying power | Yes, completed | Collective Estates | Yes, completed | Standardise and consolidate non-clinical support services | Yes, completed | Consolidate clinical support services | Yes, completed | Optimise the workforce | Yes, completed | #REF! | #REF! | 0 | 0 | The current governance is focused around a Provider Collaboration Steering Group comprised of the Directors of Finance (DoF) from each provider (the structure of which is included below). The OHSEL programme is in the process of setting up a Productivity Board, which the Steering Group will be held accountable to, and will provide further direction and drive. The board will include specialist input that the system will need to draw upon as we move forward, such as Union and HR representation. Currently Martin Shaw is the overall Senior Responsible Officer (SRO) for the productivity programme. Each productivity area is then led by a Provider DoF as SRO. Within each area we have established a Subject Matter Expert (SME) lead and, to ensure input and representation from each organisation, we also identified working groups for each opportunity. | Yes, attached. See case for change document chapter 4 | Reduce costs and improve efficiency by sharing administrative and back office functions across sites, including procurement, and rationalising collective estates. | Develop and implement networking of clinical support services so as to protect and improve the quality of services to patients, while making the most efficient use of the available workforce and capacity. | Make more efficient use of the SEL healthcare workforce reducing administrative burden on frontline staff and reducing agency spend. | Continue to build and strengthen the collaborative culture that exists among SEL providers. This will mean that providers consider and promote the interests of the SEL sector as a whole, in addition to fulfilling the obligations they have to their individual organisations. | #REF! | #REF! | #REF! | Lack of dedicated resources- Currently, all resources involved carry out the work above and beyond their day-to-day tasks. This results in work not being done as quickly as it could be and the programme not having enough traction and momentum to move forward. Dedicated resources will need to be secured to mitigate this. | Funding/investment - The work is based on the assumption of receiving STF as well as obtaining additional funds from other means. If these funds are not secured, the programme may fail to run. | Existing infrastructure/agreements - Any existing agreements (e.g. fixed term contracts) may result in difficulties in making drastic changes, consolidating functions and working collaboratively as it may not be possible or may result in hefty penalties. | #REF! | #REF! | Integrated technological systems will be put in place | Ensuring access to Transformation funding | Digital health technology investment will be sourced and available | #REF! | #REF! | Lack of resources available in the system | Identify dedicated resources and ensure time is protected | 1 | Lack of investment funds | Careful budgeting and usage of available funds including STF | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | n/a | 0 | 0 | 0 | 0